## Project Charter
Project Charter for Group {1}
Project Title: {VaultEdge}
Project Manager | Buhle Magodla
Project start date: | 2025-04-08 | Project end date: | 22/08/2025
E-Commerce Business Idea Concept
VaultEdge is an e-commerce business focused on providing affordable and reliable safety equipment for homes, offices, and commercial spaces. Our mission is to empower individuals and businesses to protect what matters most through modern and cost-effective security solutions. We specialize in CCTV surveillance systems, smart access control devices, and app-controlled doorbells, supported by nationwide delivery and optional professional installation. What sets VaultEdge apart is the combination of smart technology, competitive pricing, and excellent customer service. The platform will also feature secure payments, detailed product information, and educational resources to help customers make informed decisions.
Project objectives: This section addresses how the project ties into the group's strategic e-commerce goals, and includes the project objectives that support those goals. |  |  |  | Benefits: Benefits to potential stakeholders by doing the project .
Increase accessibility to security solutions by creating bundled packages for homeowners, businesses, and institutions tailored to their needs and budgets. |  |  |  | Improves customer experience,leading to higher conversion rates and repeat purchase .
Offer a comprehensive product range of affordable, modern safety equipment, including CCTV systems, smart access control devices, and app-controlled doorbells as well as sensors. |  |  |  | Increases brand awareness and attracts a broder customer base,resulting in higher sales volume.
Develop a secure and scalable e-commerce platform that ensures customer data protection, safe transactions, and compliance with industry security standards. |  |  |  | Makes it easier for customers confidence, reducing hesitationto purchase and increasing long-term brand credibility.
Establish VaultEdge as a trusted brand through expert content, customer education, and transparent pricing that empower customers to make informed decisions. |  |  |  | Encourages customer confidence,reducing hesitation to purchase and increasing long-term
Stakeholder Requirements: |  |  |  | Project stakeholders:
Stakeholders of the VaultEdge project have clear needs. Customers want a secure, easy-to-use platform with reliable products, delivery, installation, and support. The project team needs a scalable platform with clear goals and smooth workflows. Investors expect timely delivery, budget control, and growth potential. Partners such as suppliers and installers require clear agreements and coordination whilst still being able to make a profit and grow accordingly, while the community benefits from improved safety, useful information, and job opportunities. |  |  |  | Our project stakeholders are categorised as: Customers, the Project Team, Investors and Sponsors, Partners and the Community.
Deliverables: List the core requirements of your e-commerce website. This includes functional and non-functional requirements.
Functional Requirements |  |  |  | Non-Functional Requirements
User registration and login with secure authentication |  | Delivery availability in a widespread aspect as well as the ability to choose installation of products if needed. |  | Security | Accuracy and reliabilty with orders processing.
Product catalogue displaying all products, packages,deals and services we have to offer in a way that captures the customer's eye. |  | Easy checkout and fast and secure payment systems. |  | Mobile Responsiveness as well as user friendliness for easy navigation | Scalibility
Roles and responsibilities:
Name | Surname | Student number | Role | Cellphone | Email
Buhle | Magodla | N/A | Project Manager and Frontend Developer | 0747809085
Khanya | Freddie | N/A | Backend Developer | 0632134656
Zoe | Petersen | N/A | Backend Developer | 0740969543
SerJunior | Kabongo | N/A | Tech Support | 0660683580
Keshia | Hermanus | N/A | N/A | 0635766033
Scope: |  |  |  | Out of Scope:
The project will include a product catalogue with an option to shop by brand and product details will also be available with every product displayed. There will be a packages page with packages tailored to specific needs as well as well installation available on request at an extra price. Customers are able to add products to their cart and will be taken through a quick and easy checkout and payment process. |  |  |  | The project will focus solely on selling security and safety equipment. It will not include services such as guard deployment and will not be in creation of any security products, we are only selling products.
Risks: |  |  | Constraints: |  | Mitigation:
The business may face the following risks: strong competition from established retailers and online platforms selling similar security equipment, supply chain disruptions such as stock shortages or delayed deliveries, and technical issues with the website or payment system that could affect customer trust. Additional risks include slow customer adoption of smart security products, and potential budget or resource limitations that could impact marketing, operations, or product availability. |  |  | The business is constrained by limited financial resources, reliance on reliable suppliers, and the need for ongoing investment in technology and cybersecurity. It must comply with regulatory requirements, which can increase costs and reduce flexibility. |  | The business will reduce risks by offering quality products and good customer service, using multiple suppliers to avoid stock problems, and keeping systems secure. Costs will be controlled through careful spending and marketing, and all rules and regulations will be followed.
Assumptions: Known factors about the project that are not flexible.
The project will only sell security and safety equipment, we will not be adding guard deployment because it will cause for more security to be implemented in checking whether the person is suitable to become a guard.
Comments/Notes: